{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":270,"n_cols":9,"rows_kept":270,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,1,7],[1,8,2,8],[3,0,11,0],[3,1,8,1],[9,1,10,1],[12,0,25,0],[12,1,19,1],[20,1,24,1],[26,0,37,0],[26,1,33,1],[34,1,36,1],[38,0,48,0],[38,1,43,1],[44,1,46,1],[49,0,80,0],[49,1,62,1],[63,1,76,1],[77,1,79,1],[81,0,109,0],[81,1,94,1],[95,1,106,1],[107,1,108,1],[110,0,122,0],[110,1,114,1],[115,1,121,1],[123,0,138,0],[123,1,129,1],[130,1,137,1],[139,0,159,0],[139,1,148,1],[149,1,157,1],[160,0,172,0],[160,1,170,1],[173,0,183,0],[173,1,179,1],[180,1,181,1],[184,0,194,0],[184,1,185,1],[186,1,191,1],[192,1,193,1],[195,0,214,0],[195,1,202,1],[203,1,212,1],[215,0,228,0],[215,1,216,1],[217,1,224,1],[225,1,227,1],[229,0,268,0],[229,1,242,1],[243,1,262,1],[263,1,267,1],[269,0,269,3]],"flags":["formulas_cached_only"]}
["附表                              广西特色小镇第二批核心区建设项目计划表"]
["名称","分类","项目名称","项目内容","总投资估算（万元）","计划投资（万元）",null,null,"建设时限"]
[{"$nulls":5},"2018年","2019年","2020年"]
["三江丹洲柚香小镇","产业及相关建设项目","柚子加工产业园\n","柚子产品研发加工厂、柚子产品交易展示园、配套停车场",32100,0,20000,12100,"2018-2019"]
[null,null,"侗乐天然泉水厂","矿泉水厂",5000,0,4000,1000,"2018-2019"]
[null,null,"丹洲岛古镇风貌改造工程\n","建筑风貌改造、传统街巷空间、古城民居道路改造等",15000,200,9800,5000,"2018-2019"]
[null,null,"丹洲岛整体景观提升工程","街巷景观、园林绿化、滨水岸线景观、柚林景观等",10000,200,4800,5000,"2018-2019"]
[null,null,"丹洲岛古镇核心文化游览体系构建","闽粤会馆、丹洲书院、古城楼城墙等",10000,0,6000,4000,"2018-2019"]
[null,null,"丹洲岛民居改造高端民宿项目","改造丹洲岛民居",10000,0,6000,4000,"2018-2019"]
[null,"基础设施及公共服务项目","丹洲景区配套服务升级项目","景区迎宾大门、渡船渡轮升级、渡船码头修建改造、环岛观光自行车道、柚林生态园步道",5000,200,2800,2000,"2018-2019"]
[null,null,"丹洲岛基建设施完善改造项目","环岛防洪堤修建、垃圾处理中心、公共卫生间、民居区路灯路牌、给排水供电改造",5000,200,2800,2000,"2018-2019"]
[null,"合计",null,null,92100,800,56200,35100]
["灵川漓水文化小镇","产业及相关建设项目","古镇风情体验园","五里商业古街、漓水圩集、古圩文化广场、创客民宿等",5573,1825.9,2100,1647.1,"2018-2020"]
[null,null,"漓水文创产业园","漓水文化剧场、非遗文创街、文创孵化中心、文创精品电商中心、滨水休闲风情街、滨水主题公园",29238,0,12000,17238,"2019-2020"]
[null,null,"漓水旅居风情园","旅游集散中心、山水大境旅居度假村",35330,12000,10000,13330,"2018-2020"]
[null,null,"漓水人家","手工艺文化街、农家风情小院、得月楼",40938,21000,10000,9938,"2018-2020"]
[null,null,"漓水农耕体验园","田园民宿、都市农夫体验基地、清境竹林生态园",3508.5,0,1300,2208.5,"2019-2020"]
[null,null,"漓水生态休闲园","艺术家工作村、滨水风情民宿、生态露营基地",7200,0,3200,4000,"2019-2020"]
[null,null,"山水人文度假中心","9大主题酒店群、22大主题商业部落",180412,12000,56000,112412,"2018-2020"]
[null,null,"田园生态度假营地","体育公园部落、中医药种植园、农业体验园部落、婚礼部落、营地部落、创作基地部落、亲子乐园部落",126630,31250,53000,42380,"2018-2020"]
[null,"基础设施及公共服务项目","大圩古镇码头修复项目","修复大圩古镇码头",800,0,240,560,"2019-2020"]
[null,null,"大圩古镇雨污分流管网","设计大圩古镇雨污分流系统，防止古镇内涝，保护古镇卫生环境",500,400,100,0,"2018-2019"]
[null,null,"大圩古镇慢行步道改造项目","道路配建绿化、太阳能路灯",3000,0,500,2500,"2019-2020"]
[null,null,"漓江水文化小镇游客服务中心","新建游客服务中心及园区道路、广场、生态停车场、配建园林景观及附属设施",5000,0,500,4500,"2019-2020"]
[null,null,"大圩古镇建筑风貌改造","统一建筑风貌，修复建筑外立面",500,100,200,200,"2018-2020"]
[null,"合计",null,null,438629.5,78575.9,149140,210913.6]
["永福罗汉果小镇","产业及相关建设项目","研发楼","包括深加工研发中心、无糖食品研发中心、罗汉果商业街、AAA景区游客中心、小镇服务中心",3000,2000,1000,0,"2017-2019"]
[null,null,"人才公寓","产业人员的住宅区",6000,2000,3500,500,"2018-2020"]
[null,null,"标准厂房","产业生产厂房",9600,4000,5000,600,"2018-2020"]
[null,null,"交易市场","建设罗汉果鲜果、生果交易市场",3075,0,2000,1075,"2018-2020"]
[null,null,"豪文学校","新建学校",42000,20000,12000,10000,"2018-2020"]
[null,null,"工人疗养院","新建工人疗养院",30000,20000,10000,0,"2017-2019"]
[null,null,"罗汉果展示馆","新建展示馆",2000,900,1100,0,"2018-2019"]
[null,null,"民俗文化街","特色文化街区",32800,50,15000,17750,"2018-2020"]
[null,"基础设施及公共服务项目","凤鸣湖广场","公共配套建设、景观改造、环境改造、水系改造",50000,10000,30000,20000,"2018-2020"]
[null,null,"长江路","道路建设",1600,0,1000,600,"2018-2020"]
[null,null,"木兰街给水管道工程","新建给水管道",949,949,0,0,2018]
[null,"合计",null,null,181024,59899,80600,50525]
["荔浦衣架小镇","产业及相关建设项目","衣架产品研发展示交易中心","衣架产品研发及检验中心、衣架会展中心、衣架生产专业技术人员培训基地、配套综合服务区",62000,24800,24800,12400,"2018-2020"]
[null,null,"联动产业科研培训基地","培训楼及配套",15000,0,8000,7000,"2019-2020"]
[null,null,"农产品交易中心","新建交易中心",10000,0,6000,4000,"2019-2020"]
[null,null,"家居用品交易中心","物流配送、产品展览、交易等设施建设",12000,0,8000,4000,"2019-2020"]
[null,null,"产品质检中心","新建办公场所、产品质量检验中心",8000,0,4000,4000,"2019-2020"]
[null,null,"产业孵化园","孵化楼及配套",25000,0,10000,15000,"2019-2020"]
[null,"基础设施及公共服务项目","综合服务中心","旅游接待、商务办公、餐饮、小型会议等设施",8000,0,5000,3000,"2019-2020"]
[null,null,"民俗博物馆","新建民俗文化博物馆",11000,0,3000,8000,"2019-2020"]
[null,null,"创新创业基地","新建创业大楼及配套",7000,0,2000,5000,"2019-2020"]
[null,"其他建设项目","荔浦荔江国家湿地公园","湿地养护、河道修复、水体修复等工程",55000,22000,22000,11000,"2018-2020"]
[null,"合计",null,null,213000,46800,92800,73400]
["恭城月柿小镇","产业及相关建设项目","甜蜜柿业核心示范园（一期）","甜蜜柿业示范园建设、碗仔塘天然水库及周边栈道提升工程",2400,550,1850,0,"2018-2019"]
[null,null,"月柿研究所","建设科研室、月柿科教学堂、科研人才中心等",800,200,400,200,"2018-2020"]
[null,null,"种苗培育基地（一期）","种苗仓库、育苗研究基地、水肥管理等",4000,300,1500,200,"2018-2020"]
[null,null,"生态恭城月柿示范园提升项目","标准化生产示范点建设及诱虫灯、诱捕器、粘虫板等配套",1000,300,400,300,"2018-2020"]
[null,null,"月柿科技产业园","包括月柿绿色科技产业园、管理中心、展示区、培训中心、冷链物流区、果品分级站、质量检测站、预冷、商贸综合服务中心、冷库、道路及配套设施",76000,16000,30000,30000,"2018-2020"]
[null,null,"龙头企业培育工程","建设冷库、脱涩罐、烘干等",7000,1000,3000,3000,"2018-2020"]
[null,null,"月柿乡村电商及交易中心","电商办公交易中心、互联网交易中心建设、配套物流仓储设施",15000,3000,6000,6000,"2018-2020"]
[null,null,"中国柿子博物馆","新建博物馆",600,200,400,0,"2018-2019"]
[null,null,"月柿商业街","商业街区建设",5000,500,3500,1000,"2018-2020"]
[null,null,"市场提升项目","老市场提升改造工程",2000,1000,1000,0,"2018-2019"]
[null,null,"地标建设","莲花镇路口的标志建设",220,220,0,0,"2018-2018"]
[null,null,"红岩4A级景区项目","红岩景区游客服务中心、月柿节舞台、文化广场工程",500,500,0,0,"2018-2018"]
[null,null,"新奇特果园","新建果园及配套设施项目",800,200,600,0,"2018-2019"]
[null,null,"月柿主题文化街区","实施镇区一、二、三街月柿主题文化街区风貌改造",6000,6000,0,0,2018]
[null,"基础设施及公共服务项目","生态停车场","生态停车场、公厕、标识系统等建设",300,300,0,0,2018]
[null,null,"平江河水系开发及治理","实施平江河水系开发、生态驳岸修复、河道清淤工程",800,800,0,0,2018]
[null,null,"镇区生态治理项目","完善镇区垃圾中转站、污水处理站建设、绿化等",350,350,0,0,2018]
[null,null,"老舞台民俗文化广场提升改造","实施老舞台民俗文化广场提升改造工程",200,200,0,0,2018]
[null,null,"体育公园建设","新建体育公园",500,500,0,0,"2018-2019"]
[null,null,"市政设施提升改造（一期）","人饮工程、人行道铺设、集镇市场等公共设施完善",1200,1200,0,0,2018]
[null,null,"地下管线铺设工程","集镇内通信、电力、给排水及消防工程",3000,3000,0,0,2018]
[null,null,"月柿大道提升改造","道路提升改造",1500,1500,0,0,2018]
[null,null,"智慧城市电子商务建设","智能旅游系统、停车系统、智慧中心等建设",3000,3000,0,0,2018]
[null,null,"路网提升改造及养护项目","实施镇区道路改扩建工程",700,700,0,0,2018]
[null,null,"医疗教育设施建设","实施莲花镇民族小学、初中、高中、莲花镇民族卫生院提升改造工程",800,800,0,0,2018]
[null,null,"“宜居乡村”工程","实施东寨至岩口人居环境扩面工程及宜居乡村建设工程",2000,1800,200,0,"2018-2019"]
[null,null,"平江河水系开发","平江河（莲花河）水系漂流及旅游栈道、驿站、桥涵建设",1000,400,600,0,"2018-2019"]
[null,null,"旅客集散中心","莲花镇旅客集散中心、生态停车场、客运站等项目建设",800,200,600,0,"2018-2019"]
[null,"其他建设项目","田园产业发展提质工程","实施平江河（莲花河）两岸产业发展提质工程",500,100,200,200,"2018-2020"]
[null,null,"世界乡村之窗田园综合体","骑行道拓宽工程、驿站建设、游客服务中心、泰国康养风情村、中国月柿主题康养村等主题田园综合体建设",12000,1000,7000,4000,"2018-2020"]
[null,null,"风貌提升改造及开发项目（一期）","村落建筑风貌提升改造、交通建设、村落特色化打造、旅游体验项目建设等",10000,1000,6000,3000,"2018-2020"]
[null,"合计",null,null,159970,46820,63250,47900]
["苍梧县六堡茶小镇","产业及相关项目","六堡茶创意园","创意园及其配套",30000,5000,10000,7000,"2018-2020"]
[null,null,"交易展示中心","新建茶产品展示销售中心",2600,0,0,1300,2020]
[null,null,"六堡茶种苗培育基地","六堡茶老茶树种植、改良研究基地",2000,0,500,700,"2019-2020"]
[null,null,"六堡茶质量监督检验中心","六堡茶质量认证中心",3000,0,0,1500,2020]
[null,null,"六堡茶仓储物流中心","茶叶仓储厂房及物流基地",10000,0,5000,5000,"2019-2020"]
[null,null,"企业总部办公楼","新建办公楼",3000,0,500,1500,"2019-2020"]
[null,null,"科研中心","新建科研中心",3000,0,500,1500,"2019-2020"]
[null,null,"人才公寓工程","新建住宅公寓",2000,0,500,700,"2019-2020"]
[null,null,"六堡茶产学研基地","六堡茶茶树研究基地、苗木基地、观光茶廊等",2000,0,500,1500,"2019-2020"]
[null,null,"茶文化商业街","依托旧镇区改造的六堡茶购物街",8000,0,3000,5000,"2019-2020"]
[null,null,"滨水商业街区","核心区滨水商业街打造",12000,0,3000,6000,"2019-2020"]
[null,null,"六堡茶展示体验馆","新建展示体验馆",900,0,900,0,2019]
[null,null,"六堡茶博物馆","修建六堡博物馆",2000,0,500,1500,"2019-2020"]
[null,null,"特色文化项目","新建六堡茶水上演出剧场、瑶家风情演艺剧场",1100,0,1100,0,2019]
[null,"基础设计及公共服务项目","启动区基础设施","三通一平、路网、管网、电力、绿化等工程",8000,0,5000,3000,"2019-2020"]
[null,null,"六堡镇棚户区改造工程","棚户区改造",6500,4000,2500,0,"2018-2019"]
[null,null,"公厕建设","新建公共厕所",550,0,200,350,"2019-2020"]
[null,null,"生态停车场建设","新建生态停车场",800,0,200,600,"2019-2020"]
[null,null,"镇区给水管网工程","管网铺设",300,0,0,300,2020]
[null,null,"给水厂扩建工程","扩建水厂",600,0,0,600,2020]
[null,null,"镇区排污管网工程","新建排污管网",1000,0,0,1000,2020]
[null,null,"游客服务中心","新建游客接待中心",750,0,750,0,2019]
[null,null,"茶船古道景观工程及六堡河水系生态治理工程","河道整治及新建风雨桥，索道桥，古道两岸景点及亲水观景平台",16000,0,6000,5000,"2018-2020"]
[null,null,"滨江景观项目","新建沿河景观步道，护坡绿化等",1000,0,0,1000,2020]
[null,null,"茶船古道文化广场","文化休闲广场、六堡镇集聚中心",300,0,0,300,2020]
[null,null,"绿化工程","国道及镇区绿化",500,0,150,350,"2019-2020"]
[null,"其他项目","安置区建设工程","安置房建设",5000,0,2000,3000,"2019-2020"]
[null,null,"盆龙村村庄改造","村庄外立面改造",500,150,350,0,"2018-2019"]
[null,"合计",null,null,123400,9150,43150,48700]
["防城金花茶小镇","产业及相关建设项目","场地平整","金花茶加工园区一期场地平整",300,0,300,0,"2019-2020"]
[null,null,"华石林场场部改造","场部棚户区改造",2000,0,1000,1000,"2019-2020"]
[null,null,"金花茶加工园区一期厂房建设","新建面积约5.4万平方米厂房，购买设备",24800,0,12400,12400,"2019-2020"]
[null,null,"创意研发基地","购置设备",5000,0,2000,3000,"2019-2020"]
[null,null,"金花茶种植基地","1000亩种植基地",7000,0,3500,3500,"2019-2020"]
[null,"基础设施及公共服务项目","综合服务中心","建设游客集散中心",4200,0,4200,0,"2019-2020"]
[null,null,"旅游停车场","新建停车场",300,0,300,0,"2019-2020"]
[null,null,"启动区道路建设","新建、扩建道路",1300,0,650,650,"2019-2020"]
[null,null,"商业街区","建设美食购物街",9800,0,4900,4900,"2019-2020"]
[null,null,"金花茶康养服务总部","新建服务总部",8900,0,5000,3900,"2019-2020"]
[null,null,"滨水康养度假区（那湾水库）","新建度假区",4200,0,3300,900,"2019-2020"]
[null,null,"金花茶康养会所（那湾水库）","新建康养会所",3200,0,2200,1000,"2019-2020"]
[null,"合计",null,null,71000,0,39750,31250]
["东兴江平京族海洋小镇","产业及相关建设项目","渔港码头","建设渔港码头",200000,0,0,200000,"2018-2020"]
[null,null,"海产品检验检疫中心","海产品检验检疫中心",20000,0,0,20000,"2018-2020"]
[null,null,"储藏冷库","储藏冷库",33000,0,0,33000,"2018-2020"]
[null,null,"物流中心","物流中心",40000,0,0,40000,"2018-2020"]
[null,null,"商务办公大楼","办公大楼及配套设施",10000,0,0,10000,"2018-2020"]
[null,null,"航道疏浚工程","航道疏浚",10000,0,0,10000,"2018-2020"]
[null,null,"滨海度假酒店","建设滨海度假酒店",30000,0,0,30000,"2018-2020"]
[null,"基础设施及公共服务项目","游客中心","游客中心及配套设施建设",132,0,132,0,"2018-2020"]
[null,null,"京族哈亭荷塘景观项目","建设京族哈亭荷塘景观",142,0,142,0,"2018-2020"]
[null,null,"南国雪原景区恢复","南国雪原景区恢复工程",350,0,350,0,"2018-2020"]
[null,null,"巫头村大村房屋立面改造项目","巫头村大村房屋立面改造",450,0,450,0,"2018-2020"]
[null,null,"巫头村雨污项目","巫头村雨污分流排污排水管道建设",300,0,300,0,"2018-2020"]
[null,null,"污水处理池项目","集中生活污水处理池建设",150,0,150,0,"2018-2020"]
[null,null,"健身步道项目","健身步道建设",110,0,0,110,"2018-2020"]
[null,null,"景观节点改造","景观节点改造",90,0,0,90,"2018-2020"]
[null,"合计",null,null,344724,0,1524,343200]
["平南节庆装饰品小镇","产业及相关建设项目","保利高节庆饰品基地","节庆装饰产品、吹气塑胶制品生产车间和产品展示区域",100000,40000,30000,30000,"2018-2020 "]
[null,null,"配套企业基地","产业链上下游集聚场所",28110,0,13000,15110,"2019-2020 "]
[null,null,"物流仓储基地","物料存储区和转运场所",41198,10000,21198,10000,"2018-2020 "]
[null,null,"产品质检中心","产品质检场所及相关配套设施",10722,722,5000,5000,"2018-2020 "]
[null,null,"工业管委会","提供行政办公场所及相关配套设施",4075,0,4075,0,2019]
[null,null,"关联产业项目","装饰纺织业、新型材料化工、建材业等关联企业项目建设",94366,0,50000,44366,"2019-2020 "]
[null,null,"服务中心","服务中心建设",5757,0,1000,4757,"2019-2020 "]
[null,null,"研发孵化中心","研发中心建设",6508,0,0,6508,2020]
[null,null,"人才培训中心","培训大楼及配套",4926,0,600,4326,"2019-2020 "]
[null,null,"创客街区","文化创意街区建设",7243,0,0,7243,2020]
[null,"基础设施及公共服务项目","污水处理厂","新建污水处理厂",4234,4234,0,0,2018]
[null,null,"幼儿园","幼儿园建设",517,0,0,517,2020]
[null,null,"邻里中心","新建居民医疗、商业、文体等设施",6414,0,0,6414,2020]
[null,null,"综合市场","商业购物市场",8665,0,3000,5665,"2019-2020 "]
[null,null,"蓝领公寓","工人公寓大楼",23166,12000,9000,2166,"2018-2020 "]
[null,null,"小镇市政道路工程","新建道路、排水排污、绿化、照明等",8640,4500,4140,0,"2018-2019 "]
[null,null,"江滨休闲带项目","新建多功能公园",3563,0,2000,1563,"2019-2020 "]
[null,null,"人才公寓","优秀人员的住房小区及相关配套设施",5794,3000,2794,0,"2018-2019 "]
[null,null,"中心公园","新建市民公园",676,0,0,676,2020]
[null,null,"文创公园","节庆主题公园",208,0,0,208,2020]
[null,"合计",null,null,364782,74456,145807,144519]
["北流市民安镇陶瓷小镇","产业及相关建设项目","智能化高档陶瓷生产基地","建设多条现代、高技、自动化高端陶瓷生产线",12000,5000,4000,3000,"2018--2020"]
[null,null,"陶瓷产品质量检测中心","建设质量检测中心",6000,2000,2000,2000,"2018--2020"]
[null,null,"小镇运营管理中心","新建管理中心",2000,500,500,1000,"2018--2020"]
[null,null,"陶瓷工程技术研发中心","建设研究室、办公楼及配套设施",17000,5000,5000,7000,"2018--2019"]
[null,null,"陶瓷博物馆","建设陶瓷博物馆",3000,3000,0,0,"2018--2019"]
[null,null,"世界陶瓷之窗","陶瓷展览厅",5500,5500,0,0,"2018--2019"]
[null,null,"企业家会所","行业信息交流集散中心",1000,400,300,300,"2018--2020"]
[null,null,"小镇会客厅","游客接待服务中心、展示中心等",1500,900,300,300,"2018--2020"]
[null,null,"陶瓷文化街","包括陶艺集市、主题餐厅等内容",3500,3500,0,0,"2018--2019"]
[null,null,"陶瓷文化体验中心","包括陶艺学园、陶瓷品牌店等",3000,2000,1000,0,"2018--2019"]
[null,null,"陶瓷艺术大师工作室","创立国内外陶瓷艺术大师工作室",500,300,200,0,2018]
[null,"基础设施及公共服务项目","道路工程","道路、市政建设",25300,10000,8000,7300,"2018--2020"]
[null,"合计",null,null,80300,38100,21300,20900]
["玉州区仁厚镇中医药文化小镇","产业及相关建设项目","大参林医药集团股份有限公司饮片加工项目","建设标准化厂房、仓库及办公生活设施等",62000,30000,20000,12000,"2018 --2020 "]
[null,null,"广西玉林制药集团有限责任公司整体搬迁入园项目","建设标准化厂房、仓库及办公生活设施等",100000,30000,50000,20000,"2018 --2020 "]
[null,null,"民众中药饮片加工项目","建设标准化厂房、宿舍楼、研发中心等",50000,25000,15000,10000,"2018 --2020 "]
[null,null,"平安堂中药提取和中药饮片生产线建设项目","建设仓库、研发中心等设施",30000,10000,15000,5000,"2018 --2020 "]
[null,null,"玉林中药药健康产业园标准厂房项目","建设标准化厂房、仓库及办公生活设施等",15000,9000,4000,2000,"2018 --2020 "]
[null,null,"洋平石斛科技园-综合厂房","建设标准化厂房、仓库及办公生活设施等",15000,10000,3000,2000,"2018 --2020 "]
[null,null,"建设中医药文化展馆","建设中医药文化展馆",400,0,400,0,2019]
[null,"基础设施及公共服务项目","镇区道路工程","新建仁厚大道、康旺路、产业园道路及配套设施等",13701,13701,0,0,"2018 --2020 "]
[null,null,"公园项目","建设公园",400,0,400,0,2019]
[null,"其他项目","小镇风貌改造","小镇风貌改造",150,0,0,150,2020]
[null,"合计",null,null,286651,127701,107800,51150]
["黄姚昭平县旅游文化小镇","产业及相关建设项目","黄姚文化中心","建设会议室、演员排练室等",8000,3750,4250,0,"2018-2019"]
[null,null,"民居综合整治项目","风貌改造",1200,700,500,0,"2018-2019"]
[null,"基础设施及公共服务项目","黄姚中学迁建项目","搬迁新建学校",37461,14000,9638,5000,"2017-2020"]
[null,null,"古镇核心区污水综合整治","污水整治",4600,1600,3000,0,2019]
[null,null,"黄姚古镇旅游文化产业区路网项目","建设路网及配套",72000,9000,28000,35000,"2018-2020"]
[null,null,"黄姚古镇环境整治工程","黄姚古镇东门楼前环境整治、黄姚古镇南门楼环境整治",240,100,140,0,"2018-2019"]
[null,null,"黄姚镇康养服务中心建设","黄姚镇康养服务中心建设",300,0,100,200,"2019-2020"]
[null,null,"四方广场建设","新建广场",500,0,0,500,2020]
[null,"其他建设项目","黄姚明珠项目","土建、给排水程、电气、绿化、场地硬化及室外道路工程等",9407,4000,3000,0,"2017-2019"]
[null,null,"黄姚恒达业务楼项目","业务楼及配套设施建设",1000,1000,0,0,"2018-2019"]
[null,"合计",null,null,134708,34150,48628,40700]
["龙州边贸小镇","产业及相关建设项目","冷链物流项目","建设冷链物流",30000,0,5500,24500,"2018-2020"]
[null,null,"坚果加工项目","坚果加工生产线及食品冷链等",117000,60000,30000,15000,"2018-2020"]
[null,null,"糖果加工项目","建设硬糖、软糖、棉花糖等糖果加工生产线",25000,0,10000,15000,"2018-2020"]
[null,null,"电子加工项目","建设年产3000万条电子线束项目",3000,3000,0,0,2018]
[null,null,"新能源项目","建设年产3亿Ah新型锂动力电池生产线",6000,3000,3000,0,"2018-2020"]
[null,null,"水口边贸扶贫产业园标准厂房项目","包括边贸扶贫产业园标准场房一期（赞美加工厂）、二期标准厂房、大德亚内（一、二期）",50000,24000,26000,0,"2018-2019"]
[null,null,"二桥口岸 ","口岸大楼",5000,0,0,5000,"2020-2020"]
[null,null,"联检广场（待检区）","货物集散中心、集散广场",6000,0,0,6000,"2020-2020"]
[null,"基础设施及公共服务项目","水口边贸扶贫产业园南区路网工程","道路及相关配套",36000,0,5000,26000,"2018-2020"]
[null,null,"东盟大道","道路建设",60000,40000,15000,5000,"2018-2020"]
[null,null,"水口二桥监管区项目","国门大楼、报关报检大楼、查验平台、冻库、检疫处理区等",20000,null,5000,15000,"2018-2020"]
[null,null,"边境经济合作区水口市场 ","场地硬化、围网、联检办公用房等",18000,0,6000,12000,"2018-2020"]
[null,null,"边境经济合作区秀水路道路工程","道路、照明、绿化等",4100,1100,3000,0,2018]
[null,null,"水口边贸扶贫产业园标准厂房项目（三期）","厂区道路、厂房等 ",8000,0,1000,7000,"2018－2019"]
[null,null,"水口水厂（洞桂水厂）","水厂、管网",3000,3000,0,0,2018]
[null,null,"水口园区排污排水工程","排污管网等 ",1000,0,500,500,2018]
[null,null,"水口边贸扶贫产业园污水处理厂及配套管网工程","水污水厂1座及污水收集管网",12000,0,2500,9500,"2019－2020"]
[null,null,"污水提升泵站工程","管网和泵站",350,350,0,0,2018]
[null,"其他建设项目","中越边贸特色商业街","街区、风貌建设",8000,2000,3000,3000,"2018-2020"]
[null,"合计",null,null,412450,136450,115500,143500]
["江州区甜蜜小镇","产业及相关建设项目","经济产业园标准厂房集中区项目","新建钢筋混凝土结构标准厂房及配套用房",15000,2500,5000,3000,"2018-2020"]
[null,null,"如意岛旅游综合开发项目（一期）","建设接待区、餐厅、咖啡吧、商业展示区、酒店、养生度假公寓及配套设施等",13000,5000,3000,5000,"2018-2020"]
[null,"基础设施及公共服务项目","经济产业园新和片区路网项目（一期）","道路建设",12000,2000,5000,5000,"2018-2020"]
[null,null,"蔗糖循环经济产业园给水工程","新建自来水厂，包括净水处理厂、取水泵房、二级泵房、化验、消毒车间、管理用房等",12000,500,5000,6150,"2018-2020"]
[null,null,"经济区劳务用工实训基地项目","包括实训中心及配套",2000,1500,500,0,"2018-2019"]
[null,null,"中越边境经济合作区游客服务中心项目","新建游客服务楼及配套",2300,1600,700,0,"2018-2019"]
[null,null,"国际·如意岛体育休闲公园（中型）项目","新建羽毛球、乒乓球、棋牌、健身步道及健身路径等体育场地设施",300,100,200,0,"2018-2019"]
[null,null,"体育休闲公园（大型）项目","新建篮球、气排球、足球、健身步道等体育场地",500,200,300,0,"2018-2019"]
[null,null,"蔗糖循环经济产业园孔香工业大道项目","新建道路",14905,2800,7415,4690,"2018-2020"]
[null,null,"中越边境经济合作区示范项目（一期）道路工程","新建道路",7510,100,4410,3000,"2018-2020"]
[null,"其他建设项目","华侨商业街项目","新建商业街及配套",2600,500,2100,0,"2018-2019"]
[null,null,"华侨大道沿街外立面改造项目","华侨大道沿街房屋外立面改造",816,300,516,0,"2018-2019"]
[null,null,"蔗糖循环经济产业园周边配套","场地硬化、标志牌、围墙、便道等",400,400,0,0,2018]
[null,"合计",null,null,83331,17500,34141,26840]
["广西农垦芳香小镇","产业及相关建设项目","母猪场建设项目","新建1万头母猪场及其配套设施",33000,26000,7000,0,"2018—2019 "]
[null,null,"标准化合同育肥场项目","新建标准化合同育肥场",10000,2000,3000,5000,"2018—2020 "]
[null,null,"猪饲料厂","扩建年产40万吨饲料的猪饲料厂",3000,0,3000,0,2019]
[null,null,"永新源“冷鲜肉”初加工项目","新建冷鲜肉初加工产业链",1000,0,0,1000,2020]
[null,null,"那梭母猪场项目","建设1.1万头母猪生产线及配套设施",20000,5000,15000,0,"2018—2019 "]
[null,null,"标准化合同育肥场(配套那梭猪场)","新建标准化合同育肥场",13000,2000,5000,6000,"2018-2020 "]
[null,null,"兽医技术中心"," 对原有兽医中心进行改造",1080,500,580,null,"2018-2019 "]
[null,null,"科研孵化基地","建设孵化基地",1125,null,530,595,"2019-2020 "]
[null,null,"制糖物联网控制中心","建设物联网技术应用中心",450,450,0,0,2018]
[null,null,"广西糖业研发中心","建设糖生物化工、制糖副产品综合利用等研究中心",250,250,0,0,2018]
[null,null,"智能工厂升级改造项目","对压榨车间、制糖车间、电网直供电系统、自控系统等车间工段进行改造",1000,0,600,400,"2019-2020 "]
[null,null,"多功能仓储中心一、二期","建设仓库、冷库、果蔬分拣车间、冷鲜肉无菌加工车间等",4500,0,2500,2000,"2019-2020 "]
[null,null," 物流集散中心一、二期","建设物流集散中心",2400,0,1000,1400,"2019-2020 "]
[null,null," 大型停车场（仓储物流区）一、二期","建设停车场",600,0,300,300,"2019-2020 "]
[null,"基础设施及公共服务项目","核心区配套设施","游客接待中心、小镇景观门楼、生态停车场等",836,89,642,105,"2018-2020 "]
[null,null,"农贸市场","主要建设标准化市场、商铺",1103,0,553,550,"2019-2020 "]
[null,null,"汇香阁","建设小镇景观地标",270,0,270,0,2019]
[null,null,"芳香广场","建设广场",300,0,100,200,"2019-2020 "]
[null,null,"雕塑广场","建设以猪造型为主的植物雕塑",120,0,120,0,2019]
[null,null,"滨水健康步道","新建滨水徒步、跑步、骑行道路",450,0,150,300,"2019-2020"]
[null,null,"培训中心"," 新建技术培训中心",144,0,74,70,"2019-2020 "]
[null,null,"会议中心","新建农业论坛会议中心",216,0,100,116,"2019-2020 "]
[null,null,"特色美食街一期","新建美食街",576,0,0,576,2020]
[null,null,"文化广场","新建图书馆、农垦文化展馆",360,0,240,120,"2019-2020 "]
[null,null,"污水管网","铺设污水管网",660,0,340,320,"2019-2020 "]
[null,null,"电力及电信改造","电力架空线及电力路由",475,0,230,245,"2019-2020 "]
[null,null,"基层环卫站及休息点","新建基层环卫站及休息点",200,0,100,100,"2019-2020 "]
[null,null,"小型垃圾转运站","新建小型垃圾转运站",140,0,70,70,"2019-2020 "]
[null,null,"绿化项目","道路及建筑周边绿化",230,10,110,110,"2018-2020 "]
[null,null,"后勤办公室及管理中心项目","新建保安、保洁、工程维修等办公室及小镇管委会",528,60,468,0,"2018-2019 "]
[null,null,"行政广场","新建广场",200,0,0,200,2020]
[null,null,"中学","新建中学",300,0,0,300,2020]
[null,null,"小学（含幼儿园）","新建小学及幼儿园",300,0,0,300,2020]
[null,null,"汽车站","扩建改造汽车站",200,0,0,200,2020]
[null,"其他建设项目","横县粮食中心库","建设办公楼、仓库等 ",5500,4450,0,1050,"2018-2020 "]
[null,null,"横县病死畜禽无害化处理中心","建设病死畜禽无害化处理中心",2000,2000,0,0,2018]
[null,null,"饲料厂扩建项目","建设年产20万吨饲料生产线",3000,200,2800,0,"2018-2019 "]
[null,null,"种子仓储包装加工项目","建设办公宿舍楼、仓库和生产车间等 ",3000,3300,0,0,2018]
[null,null,"住宅风貌改造 ","原住宅小区风貌改造一、二期",800,0,400,400,"2019-2020 "]
[null,"合计",null,null,113313,46309,45277,22027]
["总计",{"$nulls":3},3099382.5,716710.9,1044867,1290624.6]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}